## Slide 1
CSC 436 — SOFTWARE PROJECT MANAGEMENT
ProTrack
Agile Software Project Management System
Introduction to Software Project Management
400-Level Computer Science | SIWES Industrial Project
[Your Full Name] • [Matric Number] • [Your University]
📌 Kanban Board
🏃 Sprint Planning
📝 Product Backlog
📈 Velocity Charts
📊 Gantt Chart
⚠️ Risk Register
👥 Team Management
💰 Cost Estimation
🔄 SDLC Models
9
Modules
47
User Stories
6
Sprints
COCOMO
II Model
ProTrack | CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio

## Slide 2
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
AGENDA
Presentation Contents
01
Problem Statement
The gap between CS theory and PM practice
02
Project Objectives
10 modules, full project lifecycle coverage
03
Agile/Scrum Framework
Sprint planning, backlog, Kanban, velocity
04
Gantt Chart & SDLC
Project timeline, WBS, and model comparison
05
Risk Management
Risk register, heat matrix, mitigation strategies
06
Team & Estimation
Roles, RACI, COCOMO II, Function Point Analysis
07
System Architecture
Technology stack, design decisions, UI patterns
08
Live Demo Highlights
Key screens from the ProTrack application
09
Testing & Validation
Test plan, test cases, quality assurance results
10
Conclusion & Future Work
Summary, SIWES alignment, next steps

## Slide 3
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 01–02 — CONTEXT
Problem Statement & Project Objectives
THE PROBLEM
Computer Science curricula teach excellent technical skills but often fail to deliver hands-on project management experience:
📋
No PM Tools
Students never use real tracking tools — Kanban, Gantt, sprint boards
📊
Theory-Only Estimation
COCOMO, FPA taught as formulas — never applied to real projects
⚠️
Risk Blind Spots
Risk management not practiced until problems already occur in industry
🏃
No Agile Exposure
Scrum ceremonies (standups, retrospectives, sprint reviews) unfamiliar
👥
Team Dynamics Gap
Project management across roles & responsibilities rarely simulated
PROJECT OBJECTIVES
Full Agile/Scrum System
Kanban, sprint planning, backlog, velocity tracking
Gantt Chart Builder
Visual project timeline with tasks, milestones, WBS
Risk Register
5-category risk matrix, mitigation strategies, heatmap
COCOMO II Calculator
Effort, duration, team size, and total cost from LOC
SDLC Model Comparison
Waterfall, Agile, Spiral, V-Model side-by-side analysis
Team Management
Role assignment, RACI matrix, workload distribution

## Slide 4
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 03 — AGILE METHODOLOGY
Agile / Scrum Framework Implementation
SCRUM CYCLE (2-WEEK SPRINTS)
Sprint Planning:
Team selects backlog items, estimates story points, sets sprint goal
Daily Standup:
15-min sync: What did you do? What will you do? Any blockers?
Sprint Review:
Demo completed features to stakeholders, collect feedback
Retrospective:
What went well? What to improve? Action items for next sprint
SPRINT VELOCITY SUMMARY
Sprint 1
May 1–14
28/28 pts
100%
Sprint 2
May 15–28
29/30 pts
97%
Sprint 3
Jun 1–14
21/34 pts
62%
KANBAN BOARD — SPRINT 3
TO DO
Build API rate limiting
Write API documentation
Burndown chart auto-update
IN PROGRESS
MFA via TOTP authenticator
Kanban drag-and-drop
API validation middleware
DONE
Sprint velocity graph
Mobile responsive layout
REST CRUD endpoints

## Slide 5
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 04 — PLANNING TOOLS
Gantt Chart & SDLC Model Selection
PROJECT GANTT CHART — PROTRACK APP (MAY–AUG 2025)
May
Jun
Jul
Aug
Requirements & Planning
Sprint 1 — Foundation
Sprint 2 — Core Features
Today
Sprint 3 — User Features
Sprint 4 — Enhancements
Sprint 5 — DevOps
Sprint 6 — QA & Deploy
UAT & Production
SDLC MODEL COMPARISON
Waterfall
Sequential
Fixed scope
Cost of change: ❌ High
Flexibility: ❌ Rigid
Agile ✓ USED
Iterative
Changing scope
Cost of change: ✅ Low
Flexibility: ✅ High
Spiral
Risk-driven
Complex/risky
Cost of change: ⚠️ Med
Flexibility: ✅ High
V-Model
Test-driven
Safety critical
Cost of change: ❌ High
Flexibility: ❌ Rigid

## Slide 6
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 05–06 — RISK & ESTIMATION
Risk Management & Cost Estimation
⚠️ RISK REGISTER
ID
Risk
Prob
Impact
Exposure
Status
R1
Key developer leaves mid-project
Med
High
HIGH
Active
R2
Scope creep from client changes
High
High
CRITICAL
Active
R3
Hosting downtime / data loss
Low
High
MEDIUM
Mitigated
R4
OAuth integration failures
Med
Med
MEDIUM
Active
R5
Team communication breakdown
Low
Med
LOW
Closed
💰 COCOMO II ESTIMATION
Project Size: 8.5 KLOC
Mode: Semi-Detached
Constants: a=3.0, b=1.12
Effort = 3.0 × (8.5)^1.12
= 3.0 × 11.58
= 34.7 person-months
Duration = 2.5 × (34.7)^0.35
= 2.5 × 3.78
= 9.4 months
Team = 34.7 / 9.4
= 3.7 ≈ 4 developers
Rate: ₦150,000/month
Cost: 34.7 × ₦150,000
= ₦5,205,000 total
BUDGET BREAKDOWN
Development 60%
₦3,123,000
Testing 15%
₦780,750
PM 10%
₦520,500
DevOps 10%
₦520,500
Buffer 5%
₦260,250

## Slide 7
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 07 — TEAM MANAGEMENT
Team Structure & Role Allocation
AO
Adebayo Olamide
Scrum Master / Backend
8
stories
48
pts done
Node.js
PostgreSQL
Scrum
CE
Chidinma Eze
Frontend / UI-UX Dev
6
stories
28
pts done
React
CSS3
Figma
IM
Ibrahim Musa
Database Admin / Backend
5
stories
31
pts done
SQL
Migrations
Redis
FA
Fatima Aliyu
Full-Stack / DevOps
5
stories
29
pts done
React
Docker
CI/CD
RACI MATRIX — RESPONSIBILITY ASSIGNMENT
Activity
Adebayo (SM)
Chidinma (FE)
Ibrahim (DB)
Fatima (DevOps)
Sprint Planning
R
A
C
I
Daily Standup
R
C
C
C
Database Design
I
I
R
A
Frontend Dev
I
R
I
C
DevOps / Deploy
I
C
I
R
Risk Management
R
C
A
I
R=Responsible A=Accountable C=Consulted I=Informed

## Slide 8
ProTrack — CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio Project
SLIDE 09 — QUALITY ASSURANCE
Testing Strategy & Validation Results
9
Modules Tested
24
Test Cases
100%
Pass Rate
A
Grade
Test ID
Test Case
Input
Expected Output
Status
TC-01
Kanban Board
User adds story to Sprint 3
Story appears in "To Do" column
PASS
TC-02
Move Card
Click card → next status
Card moves To Do→In Progress
PASS
TC-03
Sprint Progress
Stories completed = 21
Progress bar shows 62% (21/34)
PASS
TC-04
Burndown Chart
8 days remaining
Actual line shows 21 pts remaining
PASS
TC-05
Velocity Average
3 sprints: 28,29,21
Average = 26.0 pts displayed
PASS
TC-06
COCOMO Calc
8.5 KLOC, Semi-Detached
Effort=34.7, Duration=9.4, Cost=₦5.2M
PASS
TC-07
Risk Add
Fill risk form, submit
Risk appears in register with matrix
PASS
TC-08
Risk Heat Matrix
prob=High, impact=High
Cell shows CRITICAL (red)
PASS
TC-09
Gantt Today Line
Check timeline
Red dashed line on current sprint
PASS
TC-10
SDLC Comparison
View SDLC page
6 models compared in table + cards
PASS
TC-11
Team Workload
4 team members loaded
Velocity bar shows distribution
PASS
TC-12
Backlog Filter
Filter by Epic=Auth
Only Authentication stories shown
PASS

## Slide 9
SLIDE 10 — SUMMARY
Conclusion
WHAT WAS DELIVERED
Full Agile/Scrum project management dashboard
Kanban board with 4-column task pipeline
Sprint planning — 6 sprints, backlog management
Product backlog with full CRUD, filtering by epic
Velocity chart + live burndown canvas chart
Gantt chart across 8 project phases
Risk register with probability/impact heat matrix
4-member team management + RACI responsibility matrix
COCOMO II cost estimation with budget breakdown
SDLC model comparison — 6 models, 7 criteria
Persistent localStorage data storage
CSC 436 TOPICS COVERED
SDLC • Agile/Scrum • WBS • Gantt • Risk Management • COCOMO • FPA • RACI • Sprint Planning
FUTURE ENHANCEMENTS
Next Steps
Real-time Collaboration
WebSocket-based live updates — multiple users see changes instantly
AI Sprint Estimator
ML model trained on velocity data to predict sprint capacity
Jira/Trello Integration
Import/export stories from existing PM tools via API
Earned Value Management
EVM metrics: CPI, SPI, CV, SV for project health tracking
GitHub/GitLab Connect
Auto-close stories when commits reference story IDs
Thank You — Questions Welcome 📋
ProTrack | CSC 436: Software Project Management | 400-Level Computer Science | SIWES Portfolio